{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["감독자배치계획(안)"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"감독자배치계획(안)","index":0,"n_rows":10,"n_cols":13,"rows_kept":10,"cut":false,"hidden":false,"merged":[]}
["○ 공사감독자 배치계획(안)"]
[]
["* 공사명 : 평촌공업지역 스마트플랫폼 신축공사"]
["* 공사기간 : 착공 후 7개월"]
["구분(월)","23년 5월","6월","7월","8월","9월","10월","11월","12월","투입월수","환산비","환산인월수","비고"]
["건축1(총괄)","-",1,1,1,1,1,1,1,{"$f":"SUM(B6:I6)","v":7},1,{"$f":"J6*K6","v":7}]
["건축2(감독)",null,1,1,1,1,1,1,1,7,1,{"$f":"J7*K7","v":7}]
["건축3(감독)",null,1,1,1,1,1,1,1,7,1,7]
["기계1(감독)",null,null,null,1,1,1,1,1,5,1,5]
["계",{"$f":"SUM(B6:B9)","v":0},{"$f":"SUM(C6:C9)","v":3},3,4,4,4,4,4,26,null,{"$f":"SUM(L6:L9)","v":26},"총 572일·인"]