{"text_format":"2","workbook":"xls","n_sheets":1,"sheets":["2015년"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":0,"comments":5,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"2015년","index":0,"n_rows":9,"n_cols":22,"rows_kept":9,"cut":false,"hidden":false,"merged":[[0,0,0,1],[4,3,5,3],[4,6,5,6],[4,7,4,13],[4,14,4,15],[4,16,5,16],[4,17,4,20],[4,21,5,21],[3,0,4,1],[3,2,3,21],[4,2,5,2],[4,4,5,4],[4,5,5,5]],"flags":["formulas_cached_only"]}
[2015]
[]
[]
["①구분",null,"②  투자심사 내역"]
[null,null,"사업명\n(투자심사 의뢰서 기준)","분야","부문","사업개요","사업기간","사업비",{"$nulls":6}," 회계",null,"재심사여부","심사결과",null,null,null,"조건이행\n완료여부\n②-6"]
["광역","기초",{"$nulls":5},"총액","국비","시도비","시군구비","지방채","민자","기타","유형","회계명",null,"심사유형","결과","내용","유형\n②-1"]
["대전","대덕구","장동 욕골지구 새뜰마을 사업","140","142","축대 및 담장 정비 등","2015～2018",44,34,3,7,null,null,null,"일반","일반회계","신규","자체심사","적정","계획대로 추진","-","-"]
["대전","대덕구","장동고개길위험도로구조개선공사","120","121","L=1.2km, B=12m","2014~2016",40,20,null,20,null,null,null,"일반","일반회계","재심사","시의뢰심사","반려","총사업비의 25% 기지출로 재심사 제외",10,"-"]
["대전","대덕구","신탄진재정비촉진지구기반시설설치사업","140","142","녹도조성, 도로개설, 소공원, 보도육교 등","2011~2020",328,224,96,8,null,null,null,"일반","일반회계","재심사","중앙의뢰심사","반려","총사업비의 25% 기지출로 재심사 제외",10,"이행중"]